## Sheet1
Hackathon Summary
Day | Date | Task | Subtask | Owner | Start time | End time
1 | 2023-04-10 | Sprint Planning | Product Backlog | Murthy N | 10 | 10.3
|  |  | Priotorization of backlog Items | Murthy N | 10.3 | 11
|  |  | Sprint Planning Meeting | Akshay Balikai,Murthy N | 11 | 11.3
|  |  | Sprint Review | Akshay Balikai,Murthy N | 11.3 | 12
|  |  | Scrum board | Akshay Balikai | 12 | 12.3
|  |  | Sprint backlog | Murthy N | 12.3 | 12.45
|  | Data Modelling | Identified fact and dimension table | Power BI(Murthy),SQL(Prathmesh) | 1.3 | 2
|  |  | Created Cardinality | Murthy | 2 | 2.15
|  |  | Created relationships | Murthy | 2.15 | 2:45
|  |  | Data Profiling-Compared mstr and Power BI Data | Murthy | 2.45 | 3.15
|  | Report 1 | Created measures for Sales,Cost,Profit,Profit % | Akshay Waghavkar,Suraj | 3.15 | 4
|  |  | Explore on paginated report in Power BI | Prathmesh,Akshay Waghavkar, Suraj | 4 | 4.3
|  |  |  | Calculating complexity | 4.3 | 5
|  | Report 2 | Stucked column chart and table | Akshy Balikai | 3.15 | 4
|  |  | Creating measures for -Employee Head Count,Revenue Revenue Forecast Factor,Revenue per Employee | Asmita,Akash,Akshay Balikai | 4 | 5
|  | Sprint | Calculating complexity | Akshay Balikai,Murthy N | 5 | 6
|  |  | Backlog Priority | Akshay Balikai,Murthy N | 6 | 7
|  |  | Story point Estimation | Akshay Balikai,Murthy N | 7 | 8
2 | 2023-04-11 | Sprint | Scrum call | Akshay Balikai | 10 | 10.15
|  |  | Sprint defect overcome plan | AllTeam | 10.15 | 10.45
|  |  | Technical Spikes Overcome | ALL Team | 10.45 | 11
|  | Report 1 | Paginated Report | Akshay Waghavkar | 11 | 1
|  |  | Adding dax in power BI report builder using table | Suraj Dhumal | 1 | 3
|  |  | Dax ,Fixing Dax | Murthy N | 3 | 5
|  | Report 2 | Create a visual of stacked column chart with a table | Akshay Balikai | 11 | 2
|  |  | Gauge Visual | Asmita,Akash | 3 | 5
|  | Automation | Extracted the visual data from MSTR and Power BI. | Prathmesh | 6 | 7
|  |  | Imported both excel files in Python. | Prathmesh | 7 | 8
3 | 2023-04-12 | Sprint | Scrum call | Akshay Balikai | 10 | 10.15
|  | Report 1 | work on Issues related to DAX | Suraj Dhumal | 11 | 1
|  |  | grouping in report builder | Akshay Waghavkar | 1 | 3
|  | Report 2 | Distributing gauge visual into specific range and colour | Akshay Balikai | 3 | 5
|  |  | Creating same guage visual in MSTR and work around with diffrerent types of guage visual | Akash,Asmita | 11 | 2
|  | Sprint | Gromming meeting | Murthy N, Akshay Balikai | 3 | 5
|  | Automation | Created a new column using Python which is the combination of all column values separated by a delimiter. | Prathmesh | 6 | 7
|  |  | Performed string matching operation on newly created key column. | Prathmesh | 7 | 8
4 | 2023-04-13 | Sprint | Scrum call | Akshay balikai | 10 | 10.3
|  | Automation | Highlighted the difference of the rows which are common only available in source and only available in target. | Prathmesh | 10.3 | 12
|  |  | Automated the process and exported the data in excel file using Python. | Prathmesh | 12 | 2
|  | Document | Documentation of challenges faced ,assumptions, known issues and learning | Asmita | 2 | 2.3
|  | Sprint Retrospective meeting | Covered all accept ,close and conclude sprint | Akshay balikai,Murthy | 2.3 | 3

## notes
| Challenges | known Issues | POC | Assumption | Learning
Report 1 | Importing DAX into report builder Issue related to grouping in report builder | Issues related to DAX ( Showing correct results in Power bi but showing wrong result in report builder) | Created paginated report inPower builder and used Power BI service | Assumed DAX will work easily | About report builder, use of DAX in report builder, paginated report
Report 2 | 1.We needed to create a visual of stacked column chart with a table. Power BI does not have this visual 2.To address a discrepancy in the revenue forecast data between MicroStrategy and Power BI, we created a formula in Power BI that generated randomized values. However, this introduced a challenge when testing the output data against the MicroStrategy results. | 1.Combined Table and stucked column chart is not available in Power BI 2. formula for random values so data will not change . | 1.Combined table and stucked colum chart. | Assuming that in power BI there is ready to use visual which combine table and stuckedcolumn chart | How to use proper visual present in Power BI for migration
| 1.Distributing gauge visual into specific range 2.Needle in the gauge where not moving | 1.In Power BI custom guage visual don’t have moving needles and we can't distribute guage visual colour by defining range | 1.Work around different types of custom guage visual. 2.Tried with creating same guage visual in power BI 3.Revenue per employee result value is not matching in visual So Tried with creating same guage visual in MSTR and divided by 12 then its giving correct value, by this we got result as revenue is depend on month level 4.Colour gradient option is not available in power bi guage visual so we used colour fonts
Automation | 1.Source file's all rows should get compare with target file's all rows. 2.Negative values should be in round brackets with red colour font (Negative no. formatting excel) e.g. -9.9 -> (9.9) 3.Output result set values should directly get pasted in excel file. 4.Code must handle 0 vs 0.00 vs (0.00). Should handle reserve character & special characters e.g., # & ! ` ' " etc. 5.Decimals points should be considered up to 2. 6. Should be able to handle data in excels multiple worksheets (tabs). | 1.No need to change input source & target data. 2.Need to automate Mapping file location & Result file location using Python. 3.Due to random function used in Power BI, need to manually update Revenue Forcast & variance values. |  | 1.Row number should be the first column of dataset. 2.Category Source/Target column should be at start. 3.Data type of each column should be text. 4.Column names in both source and target should be same.
Project Summary

## Team Members
POWER GEARS
Akshay Balikai
Suraj Dhumal
Prathmesh Bhaik
Murthy N
Akshay Waghavkar
Asmita Gangdhar
Akash Mishra

## Sheet4
Data integration and synchronization | Power Automate can be used to integrate and synchronize data from various sources, such as SharePoint, Excel, or SQL Server, with Power BI. For example you can use Power Automate to automatically import data from a SharePoint list into Power BI, ensuring that your reports are always up to date.
Report generation and distribution | Power Automate can be used to automate the generation and distribution of Power BI reports. For example, you can set up a workflow to automatically generate a report every week and send it to a specific group of users.
Alerts and notifications | Power Automate can be used to set up alerts and notifications based on certain conditions in your Power BI data. For example, you can set up a workflow to send an email notification when a certain metric falls below a certain threshold.
Data transformation and cleansing | Power Automate can be used to transform and cleanse data before it is imported into Power BI. For example, you can use Power Automate to remove duplicates or filter out unwanted data.
Integration with other applications | Power Automate can be used to integrate Power BI with other applications, such as Dynamics 365 or Salesforce. This allows you to create a more comprehensive view of your data and streamline your business processes.
Power Automate